## Daily Report
DAILY DRILLING REPORT |  | TIME LOG (24H)
|  | From | To | Duration | Main Code | Sub Code | Description | Contractor
Well Name: | AZNS-207 | 0:00 | 6:00 | 6 | Drilling | DR-01 | Drilling 12.25in hole | Nabors
Report Date: | 2024-11-22 | 6:00 | 7:00 | 1 | Connection | CN-01 | Making connection | Nabors
Report Number: | 39 | 7:00 | 12:00 | 5 | Drilling | DR-01 | Drilling 12.25in hole | Nabors
Rig Day: | 39 | 12:00 | 13:00 | 1 | Trip | TR-01 | Trip out for bit change | Nabors
|  | 13:00 | 18:00 | 5 | Trip | TR-01 | Running new BHA | Nabors
Depth @ 00:00 | 2850 | 18:00 | 24:00 | 6 | Drilling | DR-02 | Drilling with new bit | Nabors
Depth @ 06:00 | 2875
Depth @ 24:00 | 2920

## Mud Report
MUD REPORT
Mud Weight (ppg): | 10.2
PV (cp): | 15
YP (lb/100ft²): | 10
Funnel Viscosity (sec): | 38
Gel 10s: | 4
Gel 10m: | 8
pH: | 9.5
Temperature (°F): | 120

## Survey
SURVEY DATA
MD (m) | Inc (deg) | Azi (deg) | TVD (m)
2800 | 2.5 | 45 | 2799.5
2825 | 3 | 46 | 2824.3
2850 | 3.5 | 47 | 2849
2875 | 4 | 48 | 2873.5
2900 | 4.5 | 49 | 2897.8
2920 | 5 | 50 | 2917