## DDR Remark
: | [5 empty] | Daily Drilling Report
[6 empty] | Field: |  |  |  |  | SYNF |  | Well Name: |  | SYNW-101 | Project: |  |  | SYNF |  | LTA (Day) |  |  |  | 468
[6 empty] | Well Type: |  |  |  |  | Development |  | Well Shape: |  | Vertical | Rig Name: |  |  | OEOC 900 |  | Actual Rig Days: |  |  |  | 7.25
[6 empty] | Client: |  |  |  |  | CLIENT-A |  | Operator: |  | MSA | Drilling Contractor: |  |  | OEOC |  | Report No.: |  |  |  | 8
[6 empty] | Client Rep: |  |  |  |  | P.Synth03 |  | Hole Section (inch): |  | 17-1/2" | Estimated Final Depth MD (m): |  |  | 4180 |  | Offshore Water Depth (m) |  |  |  | -
[6 empty] | GLE-MSL (m): |  |  |  |  | 3.95 |  | RTE-MSL (m): |  | 14.45 | GLE-RTE (m): |  |  | 10.5 |  | Rig Heading (°) |  |  |  | -
DATE |  |  |  | Year |  | Month |  | Day |  | MD (m)@ 0:00: |  |  | 155 |  | Drilling Operation manager: | P.Synth05 |  | Latitude: |  | 1,000,100 N |  | Previous Casing Information
Spud : |  |  |  | 2024 |  | Oct |  | 15 |  | MD (m)@ 24:00: |  |  | 225 |  | Drilling Superintendent: | P.Synth04 |  | Longitude: |  | 500,100 E |  | Size (in) | From (m) | To (m) | Grade | Weight (#) | Thread | Shoe (TVD)m | Burst (psi) | Collapse (psi)
Report: |  |  |  | 2024 |  | Oct |  | 22 |  | MD (m)@ 6:00 AM: |  |  | 310 |  | Drilling Supervisor (Day): | P.Synth02 |  | Northing (m): |  | 1000000 |  | 20" | Surface | 149 | K-55 | 94 | BTC | 149 | 2110 | 520
Hole Section Strat: |  |  |  | 2024 |  | Oct |  | 22 |  | 24 hrs Drilled (m): |  |  | 70 |  | Drilling Supervisor (Night): | P.Synth01 |  | Easting(m): |  | 500000
Moving Start Date: |  |  |  | 2024 |  | Sep |  | 30 |  | AVG. ROP (m/hrs.) |  |  | 4.6667 |  | Well Site Drilling Engineering: | - |  | KOP #1: |  | -
MW (PCF): | [7 empty] | 70 |  | RT - WH (m): |  |  | 12 |  | Well Site Geologist: | Synth08/Synth09 |  | KOP #2: |  | -
FIT Depth (MD/TVD) /EMW (PCF): | [10 empty] | Section Start Depth MD(m): |  | 151 |  | Tool Pusher Day / Night : | P.Synth06/P.Synth07 |  | Formation: |  | Aghajari
Summary of Activities in Last 24:00 hours:
Cont. Drlg 17-1/2" HS to 165m, POOH to surface, Obs. 2 No. of NZL Seat area washed out, RIH w/ 17-1/2" Drlg BHA to BTM, Commence Drlg 17-1/2" HS to 225m.
Operation Forecast for next 24 hours:
Cont. Drlg 17-1/2" HS.
From | To |  | hrs |  | Main Phase |  | Code |  | Sub Code |  | Status | NPT/ Unplan Attributed |  | Rig Activity | [8 empty] | Gain/Loss BPH |  |  | Measure Depth (m) | Time Break Down
[23 empty] | Type | MIN | MAX |  | no |  |  |  | hrs
0:00 | 6:00 |  | 6 |  | DRL |  | 2 |  | 1 |  | PLN |  |  | Cont. Drlg 17-1/2" HS f/ 155 to 165m; NL. Due to Obs. SPP Drop gradually 100 psi. Check surface line & MPs; Ok. Decided to POOH to surface. | [12 empty] | 1 | Rig Up/ Tear Down / Move
[14 empty] | Drlg Parameters: WOB: 5-10 klbs, Rot: 70-80 RPM, TQ: 1-1.5 klb.ft, F.R: 550-600GPM, SPP: 500-600psi, On BTM ROP: 2-4 MPH. | [12 empty] | 2 | Drilling |  |  | 15
6:00 | 8:00 |  | 2 |  | DRL |  | 6 |  | 6 |  | PLN |  |  | POOH w/ 17-1/2" MT Bit to surface. Obs. 2 No. of NZL Seat area washed out. Check another NZL; OK. (Bit Dull Grading: 1-1-WT-A-E-I-WO-BHA) | [12 empty] | 3 | Reaming |  |  | 1
8:00 | 14:00 |  | 6 |  | DRL |  | 6 |  | 2 |  | PLN |  |  | P/U & M/U 17-1/2" Bit (King dream, Used, 1X18/32" + 2 X Open NZL), 2 Jts 9-1/2" DC + 17-1/2" S.Stab (1/8" U.G) + 4 Jt 9-1/2" DC + X.O.S + | [12 empty] | 4 | Coring
[14 empty] | 6 Jt 8-1/2" DC + 3 Jt 5" HWDP (Jt by Jt) & Followed By 5" DP to 165m. | [12 empty] | 5 | Circulate & Condition
0.58333 | 0.89583 |  | 7.5 |  | DRL |  | 2 |  | 1 |  | PLN |  |  | Commence Drlg 17-1/2" H.S f/ 165 to 192m, meanwhile apply limited parameters until S.Stab pass 20" Shoe; NL. | [12 empty] | 6 | Trips |  |  | 8
0.89583 | 0.91667 |  | 0.5 |  | DRL |  | 3 |  | 1 |  | PLN |  |  | B/R & R/D last drilled Std. | [12 empty] | 7 | Service/ Maintain Rig
0.91667 | 0.97917 |  | 1.5 |  | DRL |  | 2 |  | 1 |  | PLN |  |  | Cont. Drlg 17-1/2" HS to 225m; NL. Pump Bentonite Hi-Vis Pill to sweep hole periodically. | [12 empty] | 8 | Repair Rig
0.97917 | 1899-12-31 |  | 0.5 |  | DRL |  | 3 |  | 1 |  | PLN |  |  | B/R & R/D last drilled Std. | [12 empty] | 9 | Replacing Drill Line
[14 empty] | Drlg. Parameters: WOB: 10-25klb, Rot:80-120 RPM, TQ: 2-4 Klb.ft, F.R:700-900 GPM, SPP: 350-600psi, ROP: 2-20 MPH | [12 empty] | 10 | Deviation Survey
[27 empty] | 11 | Logging
[27 empty] | 12 | Run Casing/ Liner
[27 empty] | 13 | Cementing
[27 empty] | 14 | Wait on Cement
[27 empty] | 15 | Rig Up/Down BOP
[27 empty] | 16 | Test BOP
[27 empty] | 17 | Drill Stem Test
[27 empty] | 18 | Fishing
[27 empty] | 19 | Specialized Directional Work
[27 empty] | 20 | Operation Status (Waiting)
[27 empty] | 21 | Safety
[27 empty] | 22 | Perforating
[27 empty] | 23 | Completion\ XMT
[27 empty] | 24 | Treating
[27 empty] | 25 | Swabbing
[27 empty] | 26 | Surface Testing
[27 empty] | 27 | Well Control
[27 empty] | 28 | Other
[27 empty] | 29 | Subsea Operation
Total |  |  | 24 | [24 empty] | Total |  |  | 24
From | To |  | hrs |  | Main Phase |  | Code |  | Sub Code |  | Status | NPT/ Unplan Attributed |  | Rig Activity | [8 empty] | Gain/Loss BPH |  |  | Measure Depth (m)
[23 empty] | Type | MIN | MAX
0:00 | 1:30 |  | 1.5 |  | DRL |  | 2 |  | 1 |  | PLN |  |  | Cont. Drlg 17-1/2" HS f/ 225 to 250m; NL. Meanwhile pump Bentonite Hi-Vis Pill to sweep hole.
1:30 | 2:00 |  | 0.5 |  | DRL |  | 3 |  | 1 |  | PLN |  |  | B/R & R/D last drilled Std.
2:00 | 3:30 |  | 1.5 |  | DRL |  | 2 |  | 1 |  | PLN |  |  | Cont. Drlg 17-1/2" HS to 280 m; NL. Meanwhile pump Bentonite Hi-Vis Pill to sweep hole.
3:00 | 4:00 |  | 1 |  | DRL |  | 3 |  | 1 |  | PLN |  |  | B/R & R/D last drilled Std.
4:00 | 5:30 |  | 1.5 |  | DRL |  | 2 |  | 1 |  | PLN |  |  | Cont. Drlg 17-1/2" HS to 310 m; NL. Meanwhile pump Bentonite Hi-Vis Pill to sweep hole.
5:30 | 6:00 |  | 0.5 |  | DRL |  | 3 |  | 1 |  | PLN |  |  | B/R & R/D last drilled Std.
Drlg. Parameters: WOB: 20-30klb, Rot:100 RPM, TQ: 2-4 Klb.ft, F.R: 900 GPM, SPP: 600psi, ROP: 15-20 MPH
Total |  |  | 6.5 | [24 empty] | Total |  |  | 6.5
Input Tight Hole Points or Intervals Depth (m):
Note:
Note#01 : Geo Data Mud logging EX monitor for driller not acceptable
Note#02 : Due to sever power surges on 16-Oct-2024, some electrical appliances of mudlogging service got damaged (1No. 21" monitor, 2No. Case power, 1No. Motherboard, 1No. POE access point).
Note#03 :
Note#04 :
Note#05 :
Note#06 :
Note#07 :
Material Request |  | Needle valve and Press. gauge for Section "A" & "B" | [14 empty] | Out Standing
Received | [16 empty] | Back Load or Sent | 2No. Oring for plug tester & W.Bushing 11" 1 No. BX 155 1 No. BX 152 1 No. Press. Gauge 10k 1 No. Niddle Valve 10k to rig 901.

## DDR Data
|  | Daily Drilling Report | [17 empty] | 467
|  | OEOC 900 | [17 empty] | 6.25
7
| Well Name |  |  | SYNW-101 | Report Date | year | month | day | MUD Data |  |  |  | Mud Chemical
| Report No |  |  | 8 |  | 2024 | Oct | 22 | Report Time |  | 0:00 |  | Product Type |  | Used | Received |  | On Hand | Unit
| Drilling Data | [7 empty] | Mud Type |  | Ben. Mud |  | Bentonite |  |  |  |  | 13 | 1 MT/BB
| Bit No. |  |  | 2 |  |  |  |  | Mud Weight | Unit | 71 |  | Barite |  |  | 24 |  | 45 | 1.5 MT/BB
| Bit Rerun NO (First Run=0) |  |  | 1 | [5 empty] | PCF |  |  | Limestone | [5 empty] | 1MT/BB
| Bit Size (inch) |  |  | 17-1/2" |  |  |  |  | Funnel Vis (Sec/QT) |  | 33 |  | Salt |  | 20 |  |  | 81 | 1 MT/BB
| Bit Type |  |  | MT Bit (GAT135G) |  |  |  |  | PV (CP) |  | 7 |  | Lime |  | 17 |  | 0 | 163 | 25 KG/SX
| Bit Manufacture |  |  | KingDream |  |  |  |  | YP (lb/100ft2) |  | 15 |  | API Starch |  |  | 40 |  | 160 | 25 KG/SX
| Bit Serial No. | [7 empty] | Gel 10 s (lb/100ft2) |  | 4 |  | Caustic Soda |  | 3 | 40 |  | 54 | 25 KG/SX
| IADC Code |  |  | 135 |  |  |  |  | Gel 10 min (lb/100ft2) |  | 6 |  | Soda Ash |  |  | 40 |  | 58 | 25 KG/SX
| Bit Nozzle |  |  | Nozzle No | Nozzle size (1/32 inch) | Nozzle No |  | Nozzle size (1/32 inch) | API Fluid Loss (cc/30 min) |  | N.C |  | Xanthan Gum |  |  |  |  | 25 | 25 KG/SX
|  |  |  | 1 | 18/32" |  |  |  | Total Hardness (mg/lit) |  | 400 |  | Nut Plug (C) |  |  |  |  | 40 | 25 KG/SX
[9 empty] | Filter Cake (1/32") |  |  |  | Nut Plug (M) | [5 empty] | 25 KG/SX
|  |  |  | 2 | Open |  |  |  | Solid (% Vol) |  | 7 |  | Nut Plug (F) | [5 empty] | 25 KG/SX
[9 empty] | Chloride (mg/lit) |  | 7400 |  | Oyster Shell (C) | [5 empty] | 25 KG/SX
[9 empty] | Oil / Water (% Vol) |  | 5 |  | Oyster Shell (M) | [5 empty] | 25 KG/SX
[9 empty] | KCL (% wt) |  |  |  | Oyster Shell (F) | [5 empty] | 25 KG/SX
[9 empty] | PH |  | 10.5 |  | Limestone chips(M) | [5 empty] | 25 KG/SX
[9 empty] | Flowline Temp (°F) |  |  |  | Limestone chips(C) | [5 empty] | 25 KG/SX
| TFA ( in^2) |  |  | 4.32 |  |  |  |  | Pf / Mf |  |  |  | Limestone chips(F) | [5 empty] | 25 KG/SX
[9 empty] | Ca++ (mg/lit) |  | 320 |  | Mica (F) | [5 empty] | 25 KG/SX
| Bit Drilled (m) |  |  | 70 |  |  |  |  | MBT (lb/bbl) |  |  |  | Mica (M) | [5 empty] | 25 KG/SX
| Bit Cum. Drilled (m) |  |  | 76 | [8 empty] | Mica (C) |  |  |  |  | 80 | 25 KG/SX
| Bit Hours on Bottom |  |  | 8.5 | [8 empty] | Sodium Bicarbonate | [5 empty] | 50 KG/SX
| Bit Cum. Hrs on Bottom |  |  | 14 | [8 empty] | Anti-Foam | [5 empty] | 55 GAL/DM
| Cum.Bit Ave ROP (m/hr) |  |  | 5.4286 | [8 empty] | H2S Scavenger | [5 empty] | 55 GAL/DM
| Bit Dull Condition | [11 empty] | Citric Acid | [5 empty] | 25 KG/SX
| Bit revolution (k.rev) |  |  | 60 |  |  |  |  | Vol. Info |  |  |  | Biocide | [5 empty] | 55 GAL/DM
| Pump Liner Size (inch) |  |  | P#1 : (180mm x 12") + P#2 : (180mm x 12") + P#3 : (180mm x 12") |  |  |  |  | Vol. in Hole (bbls) |  | 218 |  | KCl |  |  |  |  | 12 | 1MT/BB
| Pump Output (gpm) |  |  | min | max | min |  | max | Total Cir. Volume (bbls) |  | 758 |  | Corrosion Inhibitor | [5 empty] | 55 GAL/DM
|  |  |  | 700 | 900 |  |  |  | Mud Lost Down Hole (bbls) |  |  |  | Oxygen Scavenger | [5 empty] | 55 GAL/DM
| Drilling Parameter |  |  | min | max | min |  | max | Mud Lost at Surface (bbls) |  | 158 |  | Pipe Lax | [5 empty] | 55 GAL/DM
| W.O.B (klb) |  |  | 10 | 30 |  |  |  | Suction 1 Vol.(bbls)/MW (PCF) |  | 270 | 71 | Bit Lube | [5 empty] | 55 GAL/DM
| Motor RPM ( rev/gal) | [7 empty] | Suction 2 Vol.(bbls)/MW (PCF) |  | 330 | 72 | Drilling Detergent | [5 empty] | 55 GAL/DM
| Surf. RPM ( rev/gal) |  |  | 80 | 120 |  |  |  | Reserve 1 Vol.(bbls)/MW (PCF) |  | 190 | 70 | Glass Bead (M) | [5 empty] | 25 KG/SX
| Torque (kft-lbs) |  |  | 2 | 4 |  |  |  | Reserve 2 Vol.(bbls)/MW (PCF) |  | 45 | 70 | Kwick Seal (M) |  |  |  |  | 80 | 25 KG/SX
| Pump Pressure (psi) |  |  | 350 | 600 |  |  |  | Reserve 3 Vol.(bbls)/MW (PCF) |  | 90 | 62
| SCR Data: | SPM | FR (GPM) | SPP |  | SPM | FR (GPM) | SPP | Reserve 4 Vol.(bbls)/MW (PCF)
| Pump No. #1 |  |  |  | Pump No. #3 |  |  |  | Middle (bbls)/PCF |  | 240 | 72
| Pump No. #2 | [7 empty] | Desilter (bbls)/PCF
| BHA No. #3 |  |  |  | BHA No. |  |  |  | Desander (bbls)/PCF |  | 95 | 71
| Item | OD (in) | Length (m) | Cum. Len | Item | OD (in) | Length (m) | Cum. Len | Degasser (bbls)/PCF |  | 95 | 71
| 17-1/2" MT Bit | 17.5 | 0.41 | 0.41 |  |  |  |  | Sand Trap (bbls)/PCF |  | 80 | 71
| 9-1/2" Bit Sub | 9.5 | 1.23 | 1.64
| 9-1/2" DC | 9.5 | 18.04 | 19.68 |  |  |  |  | Down Hole Equipment
| S.Stab | 17.5 | 2.55 | 22.23 |  |  |  |  | Equipment |  | OD (inch) |  | Serial Number |  | Rot. Hrs |  |  | Cum. Hrs
| 9-1/2" DC | 9.5 | 34.44 | 56.67 |  |  |  |  | 9-1/2" Bit Sub |  | 9.5" |  | 1515041004 |  | 8.5 |  | 14
| XOS | 9.5 | 0.78 | 57.45 |  |  |  |  | 17-1/2" S.Stab |  | 17.5" |  | 15013006 |  | 8.5 |  | 8.5
| 8-1/2" DC | 8.5 | 49.595 | 107.045 |  |  |  |  | XOS #1 / XOS #2 |  | 9 1/2" ¦ 6 5/8" |  | 9000000001 ¦ 9000000002 |  | 8.5 |  | 14
| XOS | 6.625 | 0.95 | 107.995
| 5" HWDP | 5 | 27.83 | 135.825 |  |  |  |  | Survey Data
[9 empty] | M.D (m) | Incl. | Azimuth | TVD (m) | North (m) | East (m) |  | VS / HD |  | DLS | Tool
[9 empty] | 50 | 0
[9 empty] | 108 | 0.25
[9 empty] | 146 | 0.25
| TOTAL(m) |  |  | 135.825 | TOTAL(m) |  |  | 0
| Bulk Data | [8 empty] | Weather Data |  |  | Cement and Cement Additives
| Mat. Type |  | F.W | D.W | Fuel Rig | Fuel Camp |  | Blend CMT | CMT "G" Delijan | Wind Speed (Km/h) |  |  | Material Type |  | Used | Received | On Hand | On Hand | Unit
| Unit |  | Lit | BBL | Lit | Lit |  | MT | MT | Wind Direction |  |  | FLC-DA9 / FLC-DA413 | [5 empty] | 50 lb / Sxs
| On Hand |  | 28000 | 1100 | 80000 | 6100 |  |  | 7 | TEMP(°C) |  |  | CR-DA12 | [5 empty] | 50 lb / Sxs
| Used |  | 12000 | 660 | 3000 | 700 |  |  |  | Visibility (km) |  |  | CFR-DA3 | [5 empty] | 50 lb / Sxs
| Received |  | 15000 | 360 | [5 empty] | Safety & Drills |  |  | CR-DA4 | [5 empty] | 55 lb / Sxs
| BOP Stack and Well Head | [8 empty] | Last BOP Test |  | 1403-07-30 | Microblock / Surfactant (PA-DA5) | [5 empty] | 55 Gal / DR
| Name | TYPE |  | W.P (psi) | SIZE | RAMS |  |  | Last Test | Last Fire Drill |  |  | spacer | [5 empty] | 55 lb / Sxs
[10 empty] | Last H2S Drill |  |  | Calcium chloride | [5 empty] | 55 lb/ sxs
| Annular | RS |  | 3K | 20-3/4" | - |  |  | 1403-07-30 | Last BOP Drill |  |  | Musol Solvent / Paragas | [5 empty] | 55 Gal / DR
| Double rams | U-Type |  | 3K | 20-3/4" | Blind & 5" Fix Ram |  |  | 1403-07-30 | Days Without LTA |  | 468 | Defoamer (DF-DA3) | [5 empty] | 5 Gal / Can
| Drlg Spool |  |  | 3K | 20-3/4" | - |  |  | 1403-07-30 | Personnel on Board |  |  | Formation Top Data
| Single rams | - |  | - | - | - |  |  | - | OEOC Rig |  | 76 | Name |  | m MD | m TVD |  | Lithology
Note#02 : Due to sever power surges on 16-Oct-2024, some electrical appliances of mudlogging service got damaged (1No. 21" monitor, 2No. Case power, 1No. Motherboard, 1No. POE access point). | Spacer Spool | - |  | 3K | 20-3/4" | - |  |  | 1403-07-30 | Client (KPE) |  | 3 | Aghajari |  |  |  |  | Gy Mrl, Rd Mrl, SST
| DSA Pack Off | - |  | 3K | 20-3/4" | - |  |  | 1403-07-30 | MSA |  | 7
| T.H.S | - |  | - | - | - |  |  | - | Service company |  | 14
| C.H.S | - |  | - | - | - |  |  | - | Catering + Guard |  | 22
| C.H.H | MSP/DRILEX |  | 3K | 20-3/4" | - |  |  | 1403-07-29 | Labour |  | 8
[10 empty] | Other |  | 0
[10 empty] | Total POB |  | 130
| Solid Control | [7 empty] | Boats
| Equipment | Size/# Cones |  | U.F | O.F | Daily Hrs/ Cum hrs |  |  | Name | Arrival Rig |  |  |  | Departure |  |  |  |  | Status
| Shaker #1 | 2 x 100 + 2 x 80 API |  |  |  | 24 |  | 68 |  | Time |  | Date |  | Time |  | Date
| Shaker #2 | 2 x 100 + 2 x 80 API |  |  |  | 24 |  | 102
| Shaker #3 | 2 x 100 + 2 x 80 API |  |  |  | 16 |  | 80
D-Sander
D-Silter
| Centrifuge#1 | [7 empty] | Chopper
| Centrifuge#2 | [7 empty] | Name | Arrival Rig |  |  |  | Departure
| Mud cleaner | [8 empty] | Time | Date | No. of PAX IN |  | Time | Date |  |  | No. of PAX IN
Vac. Degasser
Note on S33: Author:

## Lookahead
Operations Lookahead - Rig Name OEOC 900 Well Name SYNW 101, P-00
SPUD THE RIG @ 15-Oct-2024, 18:00 | [7 empty] | 2024-10-22
Days | Activity |  |  |  |  | Comments
|  |  | HRs | Date Start | Date End
2024-10-22 | Drilling 17-1/2" HS to 165m. CBU & POOH to surface. |  | 14 | 2024-10-22 | 2024-10-22 14:00
2024-10-22 14:00 | RIH w/ same bit and S.Stab @ 20m to bottom & Resume Drlg 17-1/2'' HS to 220m. |  | 10 | 2024-10-22 14:00 | 2024-10-23
2024-10-23 | Cont. Drlg 17-1/2'' HS to 450m. |  | 19 | 2024-10-23 | 2024-10-23 19:00
2024-10-23 19:00 | CBU, Take Survey. |  | 3 | 2024-10-23 19:00 | 2024-10-23 22:00
2024-10-23 22:00 | Perform wiper trip. |  | 2 | 2024-10-23 22:00 | 2024-10-24
2024-10-24 | Cont. Drlg 17-1/2'' HS to 600m. |  | 24 | 2024-10-24 | 2024-10-25
2024-10-25 | Cont. Drlg 17-1/2'' HS to 750m. |  | 8 | 2024-10-25 | 2024-10-25 08:00
2024-10-25 08:00 | CBU, Take Survey. |  | 4 | 2024-10-25 08:00 | 2024-10-25 12:00
2024-10-25 12:00 | Perform wiper trip. |  | 2 | 2024-10-25 12:00 | 2024-10-25 14:00
2024-10-25 14:00 | Displace mud in hole by 72pcf KCL/Polymer mud @ 750m |  | 2 | 2024-10-25 14:00 | 2024-10-25 16:00
2024-10-25 16:00 | Cont. Drlg 17-1/2'' HS to 800m. |  | 8 | 2024-10-25 16:00 | 2024-10-26
2024-10-26 |  |  | 24 | 2024-10-26 | 2024-10-27
2024-10-27 |  |  | 24 | 2024-10-27 | 2024-10-28
Equipment To Be Sent Back: |  | 6" M.M J.Mill, 4-1/4" Taper Tap, 8-3/8" M.M.J.Mill, 8-1/2" Bit, 6-1/8" Bit, 5-7/8" Bit, 4-1/2" TP-G2 Pin X 4-1/2" IF box, 7" Circ. Swage, 7" & 4-1/2" Drift, 4-1/2" X 6-1/8" Spirolizer, 7" X 8-1/2" Spirolizer, 4 Jts 20" CSG.
Request: |  | Needle valve and Press. gauge for Section "A" & "B".
Prepared By: |  | P.Synth01 |  |  | Approved By: |  | P.Synth02
Formulas:
Days = [Date Start]
Date Start = [Date End, row above]
Date End = [Date Start]+[HRs]/24

## Service Company
Hole Section | Company | Service | Date In | Date Out | Duration (Day) | Job Description | Condition | Problem/Issue | Total NPT (HRS)
26" HS | Vira | Mud Service | Spud 15-Oct-2024
26" HS | APAD | Waste Management Service | Spud 15-Oct-2024 | [8 empty] | 467
26" | GEO Data | Mud Logging Service | Spud 15-Oct-2024 | [8 empty] | 6.25
26" HS | OEOC | CSG Running Service | 18-Oct-2024, 18:00. | 19-Oct-2024, 18:00 | 1 | Run 20" CSG | [5 empty] | 7
26" HS | SPAD Energy | CMT Service | 19-Oct-2024, 08:00. | 19-Oct-2024, 20:00 | 1 | CMT 20" CSG
26" HS | OEOC | Wellhead Crew | 19-Oct-2024, 11:00. | 20-Oct-2024, 13:30 | 3 | Install & P.T 20-3/4" C.H.H
0
Landing Jt. L/D mouse hole. Cut & L/D 30" conductor pipe. Install Base Plate & Welded same to 20" CSG. Final Cut 20" CSG, Dress & Bevel
N/U 20-3/4" BOP Stack as: 20-3/4" 3k X 3k DSA + Spacer Spool + Drlg spool + Double Rams (Blind Rams, 5" Fix Rams) + Ann Preventer.
Note#02 : Due to sever power surges on 16-Oct-2024, some electrical appliances of mudlogging service got damaged (1No. 21" monitor, 2No. Case power, 1No. Motherboard, 1No. POE access point).

## Activity Codes
| Main Phase |  | Description
| MOV | Moving | All of operation from Tear out, Rig down, …, Transportation to Rig up & Spud. |  |  |  |  | 467
| DRL | Drilling | All of operation during making a hole from surface to the target including Trips, Circulation, Drilling, Reaming, etc. |  |  |  |  | 6.25
| LOG | Logging | All of operation during taking a log from R/U logging Equip. to R/D including all of related activities same as Logging, Condition trip, Fishing, etc. |  |  | NI-015 |  | 7
| CSG | Casing/ Liner | Includes all procedures from Rig up Running Equipment, Casing/ Liner Running, Perform CMT job and R/D same. |  |  | 2021-03-29 | M1
| COM | Completion | Includes all procedures from Rig up Running Equipment, Running Completion String, Pressure Tests, Instaling XMT and Perforation Job.
| FTS | Formation Testing & Stimulation | All of operation related to Acidizing, Testing, Lifting, Well Flowing, etc.
| PIH | Pilot Hole | Drilling a small hole diameter into the formation including all related operation same as Time drilling, Logging, Coring, Plug back, etc.
| COR | Coring | The extraction from the wellbore of a cylindrical sample for geological analysis.
| REE | Re-Entry | The act of entering a plugged well for the purpose of utilizing said well for the production of oil or gas, for the disposal of fluids therein, for a service well, or for the salvaging of tubing or casing therefrom.
| ABD | Abandonment/Suspension | Including all operation to permanent or temporarily subsurface isolation to prevent any undesired communication between any distinct zones and fluid movement out of a well using validated well barriers. | 0
Code | Sub code | Code Name | Description
1 |  | Rig Up/ Tear Down / Move
| 1-1 | Rig Moving/ Positioning | Rig Moving, Spot, Positioning and verify the location.
| 1-2 | Rig Up | The on-site connection of rig components in preparation for drilling or well servicing operations. Rig up begins when the first rig components have arrived at the wellsite, and ends when the rig is ready to spud the well.
| 1-3 | Rig Down | To take apart equipment for storage and portability.
| 1-4 | Tear Out | The act of dismantling a rig at the end of a well and preparing it for moving to the next location.
| 1-5 | Rig Skid | Skid in /out Activities.
2 |  | Drilling
| 2-1 | Vertical Drilling | Vertical Drilling, with all type of BHA with or without DHM (Performane Drilling )
| 2-2 | Directional & Horizontal Drlg. (Rotating mode) | Any Directional Drilling at Rotating Mode with Directional BHA
| 2-3 | Directional & Horizontal Drlg. (Sliding mode) | Any Directional Drilling at Sliding Mode
| 2-4 | Coiled Tubing Drilling | Drilling Formation with CT. |  | Landing Jt. L/D mouse hole. Cut & L/D 30" conductor pipe. Install Base Plate & Welded same to 20" CSG. Final Cut 20" CSG, Dress & Bevel
3 |  | Reaming
| 3-1 | Reaming / Back Reaming | Any Rotating of Bit Without Making Hole. |  | N/U 20-3/4" BOP Stack as: 20-3/4" 3k X 3k DSA + Spacer Spool + Drlg spool + Double Rams (Blind Rams, 5" Fix Rams) + Ann Preventer.
| 3-2 | Wash Down | Run in Hole With Pumping
| 3-3 | Under reaming/ Hole Opening/ Hole Enlargement | Planned Opening Hole/Underreaming/ Hole Enlargment
| 3-4 | Drill Out Cement/ Shoe track | Any Vertical or Directional Drilling of Cement, Float and shoe
4 |  | Coring
| 4-1 | Trip in for Coring | P/U & M/U Equip. RIH for Coring Operation
| 4-2 | Trip out for Coring | POOH for Coring Operation, B/O & L/D Equip.
| 4-3 | Coring Operation | Coring operation and any circulating.
| 4-4 | Core Recovery | Core Recovery Period time
5 |  | Circulate & Condition
| 5-1 | Hole displacement | Mud Preparation, Displacing the hole with mud or any fluid
| 5-2 | Circulate/ Condition Mud | Sweep the well, Circulation of hole to clean hole, treat the mud condition.
| 5-3 | Coiled Tubing Ops. | Circulation of hole with CT
| 5-4 | Loss control | All Activities Associated with Circulate and Condition due to lost circulation or putting LCM plugs & CMT plug.
6 |  | Trips
| 6-1 | R/U & R/D Pipe Handling Equip. | Rig up and Rig down Pipe/BHA Handling Equipment
| 6-2 | PU/LD BHA | Preparing, Picking Up and Making Up The BHA. Break out and Laying Down BHA
| 6-3 | Pick up Drill Pipe | Picking Up The Drill Pipe, making stand and rack back same.
| 6-4 | Lay Down Drill Pipe | Disconnect and Laying Down Drill Pipe
| 6-5 | Run in Hole | Trip in hole with string or any tubular, BHA.
| 6-6 | Pull Out Of Hole | Trip out of hole with string or any tubular, BHA.
| 6-7 | POOH with Pumping | Trip Out of Hole With Pumping
| 6-8 | Wiper/ Condition Trip | The process by which the drill bit is pulled back inside the previous casing shoe and then run back to bottom.
| 6-9 | Wear Bushing | Installation or Retrieving of Wear Bushing
7 |  | Service/ Maintain Rig
| 7-1 | Rig Lubricate | Normal Lubrication and Scheduled Planned Maintenance - that shuts operations down WITHOUT contractual down time
8 |  | Repair Rig
| 8-1 | Circulating System | All repairs of rig equipment according to Circulating System
| 8-2 | Power System | All repairs of rig equipment according to Power System
| 8-3 | Hoisting System | All repairs of rig equipment according to Hoisting System
| 8-4 | Rotating System | All repairs of rig equipment according to Rotating System
| 8-5 | Well Control System | All repairs of rig equipment according to Well Control System
| 8-6 | Other | All repairs of rig equipment according to other parts.
9 |  | Replacing Drill Line
| 9-1 | Slip & Cut of Drill Line | Cut and slipping drill line with the operators consent
10 |  | Deviation Survey
| 10-1 | Performing Survey Operation | All Activities Associated With MWD, Gyro (Single shot/Multi shot), Tatco, etc.
11 |  | Logging
| 11-1 | R/U & R/D Logging Equip. | Rig up and Rig down Logging Equipment
| 11-2 | Wire line logging | All Activities Associated with Wireline Logging
| 11-3 | TLC Logging | All Activities Associated with TLC Logging
| 11-4 | CT Logging | All Activities Associated with CT Logging
12 |  | Run Casing/ Liner
| 12-1 | R/U & R/D Handling Equip. | Rig up and Rig down Casing Running Handling Equipment
| 12-2 | CSG Running | Running of Casing to shoe depth.
| 12-3 | Pulling Casing | All Activities Associated With Pulling Casing
| 12-4 | CSG/Liner Integrity Test | All Activities Associated With CIT (CSG/Liner Integrity Test )
| 12-5 | Liner Running | Liner Running and set hanger
| 12-6 | Liner Tie back Operation | Included runing Liner joints, and pulling setting tools
| 12-7 | Pull out Liner hanger setting tools and L/D | POOH T/Surf. And L/D Setting tool
| 12-8 | Other Related Casing/Liner Activities | Including inflow test, etc.
| 12-9 | Nipple up/down Wellhead | All activities related to Installing and Removing of the Wellhead.
13 |  | Cementing
| 13-1 | Casing/ Liner Cementing | Making cement solution, Mix and pump of cement slurry to the wellbore for casing/ Liner/ Tie back operation.
| 13-2 | Plug Back | Includes section/ well abandonment plugs or side track plugs.
| 13-3 | Squeeze CMT | The Process by which cement slurry is squeezed into place in order to carry out remedial work (e.g. shut off water producing zone, repair casing leaks , etc. )
| 13-4 | Balance Plug | A plug of Cement placed as a slurry in a specific location until the level of cement outside is equal to that inside the drill pipe/ workstring/ tubing.
| 13-5 | Other
14 |  | Wait on Cement
| 14-1 | for Casing/ Liner Cementing | WOC due to Casing/ Liner Cementing.
| 14-2 | for Cement plug | WOC due to Plug back/ Balance Plug/ Well Suspension/ Abandonment plugs.
| 14-4 | Other
15 |  | Rig Up/Down BOP
| 15-1 | Nipple up/down BOP | All activities related to Nippling up or nippling down the BOP and Divertors
16 |  | Test BOP
| 16-1 | Pressure Test BOPs | All activities associated with Pressure Test BOPs, Choke Manifold and Surface Equipment
17 |  | Drill Stem Test
| 17-1 | Conventional DST | All activities associated with a Conventional DST including R/U, R/D, RIH, …, POOH.
| 17-2 | Full Bore DST | All activities associated with a Full Bore DST including R/U, R/D, RIH, …, POOH.
| 17-3 | Dry test | Included Scraper trip, Run test string, Perform job & POOH.
18 |  | Fishing
| 18-1 | Fishing Job | All preparing, assembling of fishing equipment to RIH w/fishing equipement, Work on Fish and Retrieve.
| 18-2 | Milling | All activities associated with Milling.
| 18-3 | Coiled Tubing Ops. | All activities associated with CT.
| 18-4 | Work on Stuck | Stuck pipe period time including all of related logs, Back off, etc.
19 |  | Specialized Directional Work
| 19-1 | RIH/ POOH Side-Track equip. | RIH to Set Packer/ WhipStock to start Side-Tracking.
| 19-2 | Side-Tracking in Open Hole | Side Tracking Original Hole For Any Reason on wellbore wall in open hole
| 19-3 | Side-Tracking in Cased Hole | Side Tracking Original Hole For Any Reason on wellbore wall in cased hole
| 19-4 | Other
20 |  | Operation Status (Waiting)
| 20-1 | Waiting on Client | Any reason the rig prime activity is waiting due to Client
| 20-2 | Waiting on Operator Company | Any reason the rig prime activity is waiting due to Operator Company
| 20-3 | Waiting on Rig Contractor | Any reason the rig prime activity is waiting due to Rig Contractor
| 20-4 | Waiting on Service companies | Any reason the rig prime activity is waiting due to Sub Contractors
| 20-5 | Waiting on Weather | Any reason the rig prime activity is waiting due to Weather
| 20-6 | Waiting on Logistics/ Fuel | Any reason the rig prime activity is waiting due to Fuel
21 |  | Safety
| 21-1 | Pre Job Safety Meeting (PJSM) | Time period for Pre Job Safety Meeting.
| 21-2 | Drills | All activities associated with Safety Drills.
| 21-3 | Other HSE Related activities
22 |  | Perforating
| 22-1 | Wire line Perforation | All activity associated with Perforation (Preparing, R/U wire line)
| 22-2 | TCP Perforatin | All activity associated with Perforation with tubing.
| 22-3 | CT Perforatin | All activity associated with Perforation (Preparing, R/U CT BOP, Injector, etc.)
23 |  | Completion\ XMT
| 23-1 | Completion Trips | All activity associated with Completion Trips (R/U & R/D completion running tools, run/pull completion string etc.).
| 23-2 | Completion Test | All activity associated with Function test and pressure test during completion ops.
| 23-3 | Fluid displacement | Completion Fluid displacement
| 23-4 | Slick line jobs | Included shifting tolls, plug and prong running tools, etc.
| 23-5 | Coiled Tubing Ops. | All activity associated with completion done by CTU.
| 23-6 | Nipple up/down XMT | All activities related to Installing and Removing of the XMT.
| 23-7 | XMT Test | All activities associated with Pressure Test of XMT.
24 |  | Treating
| 24-1 | Acidizing | All activity associated with Acidi Job.
| 24-2 | N2 Lifting | All activity associated with N2 Lifting.
| 24-3 | Coiled Tubing Ops. | Preparing, R/U CT BOP, Injector Head, etc.
25 |  | Swabbing
| 25-1 | Swabbing
26 |  | Surface Testing
| 26-1 | Surface Testing | All activity associated with Surface well testing when completion string is in hole.
| 26-2 | Clean Up | All activity associated with Clean up operation when completion string is in hole..
27 |  | Well Control
| 27-1 | Kill the well | Kill the well with different methods.
| 27-2 | Take S.C.R | Take Slow Pump Rates
| 27-3 | FIT/ LOT | All activity associated with an F.I.T/L.O.T.
| 27-4 | Flow Check | Flow Check/Monitor Well while tripping and drilling
| 27-5 | Strip In / Out | All activity associated with an Strip In / Out.
| 27-6 | Coiled Tubing Ops. | Preparing, R/U CT BOP, Injector Head, etc.
28 |  | Other
| 28-1 | Other
29 |  | Subsea Operation
| 29-1 | Run/ Retrieve Riser Equip.
| 29-2 | Subsea Installation

## setting (hidden)
[14 empty] | DAY | Month | year | Operation type | Drilling Superintendent : | Drilling Supervisor Day: | Drilling Supervisor Night : | Well Site Drilling Engineering: | Well Site Geologist: | Rig Operations Manager /Rig Manager: | Drilling Contractor: | Tool Pusher Day / Night : | IADC CODE (BIT) | Bit Type | Mud Type
Field | bit size | CASING LINER SIZE | HOLE SECTION | Well Name | status | Rig Name | Project | Service Copmany | GAIN LOS TYPE | MW UNIT | MAIN PHASE | WELL TEYPE | WELL SHAPE | 1 | Jan | 2021 | Offshore | [8 empty] | M1365 | Type1 | Salt-Polymer
Azadegan | 32 | 32 | 32 | NI-015 | PLN | DANA-1 Rig | Belal |  | GAIN | (pcf)/ @35˚C | MOV | Development | J Shape | 2 | Feb | 2022 | Onshore | [8 empty] | M1366 | Type2 | Brine
Gachsaran | 26 | 26 | 26 | NI-016 | UNPLN | DANA-2 Rig | West Paydar |  | LOSS | PPG | DRL |  |  | 3 | Mar | 2023 | [9 empty] | M1367 | Type3 | Kcl
West Paydar | 23 | 23 | 23 | NI-017 | NPT | DANA-3 Rig | Gachsaran 3&4 |  |  |  | LOG |  |  | 4 | Apr | 2024 | [9 empty] | M1368 | Type4 | KCL-Polymer
Ramin | 17.3333 | 17.3333 | 17.3333 | NI-018 | NPT-UNPLN |  | Azadegan |  |  |  | CSG |  |  | 5 | May | 2025 | [9 empty] | M1369 | Type5
Ahwaz | 13.375 | 13.375 | 13.375 | NI-019 | [6 empty] | COM |  |  | 6 | Jun | 2026 | [9 empty] | M1370 | Type6
Farzad | 12.25 | 12.25 | 12.25 | NI-020 | [6 empty] | FTS |  |  | 7 | Jul | 2027 | [9 empty] | M1371 | Type7
Nargesi | 6 | 6 | 6 | NI-021 | [6 empty] | PIH |  |  | 8 | Aug | 2028 | [9 empty] | M1372 | Type8
|  |  |  | NI-022 | [6 empty] | COR |  |  | 9 | Sep | 2029 | [9 empty] | M1373 | Type9
|  |  |  | NI-023 | [6 empty] | REE |  |  | 10 | Oct | 2030 | [9 empty] | M1374 | Type10
|  |  |  | NI-024 | [6 empty] | ABD |  |  | 11 | Nov | 2031 | [9 empty] | M1375 | Type11
|  |  |  | NI-025 | [9 empty] | 12 | Dec | 2032 | [9 empty] | M1376 | Type12
|  |  |  | NI-026 | [9 empty] | 13 |  | 2033 | [9 empty] | M1377 | Type13
|  |  |  | NI-027 | [9 empty] | 14 |  | 2034 | [9 empty] | M1378 | Type14
|  |  |  | NI-028 | [9 empty] | 15 |  | 2035 | [9 empty] | M1379 | Type15
|  |  |  | NI-029 | [9 empty] | 16 |  | 2036 | [9 empty] | M1380 | Type16
|  |  |  | NI-030 | [9 empty] | 17 |  | 2037 | [9 empty] | M1381 | Type17
|  |  |  | NI-031 | [9 empty] | 18 |  | 2038 | [10 empty] | Type18
|  |  |  | NI-032 | [9 empty] | 19 |  | 2039 | [10 empty] | Type19
|  |  |  | NI-033 | [9 empty] | 20 |  | 2040 | [10 empty] | Type20
|  |  |  | NI-034 | [9 empty] | 21 |  | 2041 | [10 empty] | Type21
|  |  |  | NI-035 | [9 empty] | 22 |  | 2042 | [10 empty] | Type22
|  |  |  | NI-036 | [9 empty] | 23 |  | 2043 | [10 empty] | Type23
|  |  |  | NI-037 | [9 empty] | 24 |  | 2044 | [10 empty] | Type24
|  |  |  | NI-038 | [9 empty] | 25 |  | 2045 | [10 empty] | Type25
|  |  |  | NI-039 | [9 empty] | 26 |  | 2046 | [10 empty] | Type26
|  |  |  | NI-040 | [9 empty] | 27 |  | 2047 | [10 empty] | Type27
|  |  |  | NI-041 | [9 empty] | 28 |  | 2048 | [10 empty] | Type28
|  |  |  | NI-042 | [9 empty] | 29 |  | 2049 | [10 empty] | Type29
|  |  |  | NI-043 | [9 empty] | 30 |  | 2050 | [10 empty] | Type30
[14 empty] | 31 | [12 empty] | Type31
Type32
Type33
Type34
Type35
Type36
Type37
Type38
Type39
Type40
Type41
Type42
Type43
Type44
Type45
Type46
Type47